## Network Diagram
taskID | task | predecessorTaskIDs | bestCaseHours | expectedHours | worstCaseHours | projectManager | frontendDeveloper | backendDeveloper | dataScientist | dataEngineer
A | Describe product |  | 6 | 6 | 6 | 6
B | Develop marketing strategy |  | 15 | 15 | 144 | 15
C | Design brochure | A | 12 | 12 | 12 | 4 | 12
D | Develop product prototype
D1 | Requirements analysis | A | 18 | 18 | 24 | 8 |  | 8 | 8
D2 | Software design | D1 | 4 | 25 | 49 | 4 |  | 15 |  | 10
D3 | System design | D1 | 25 | 25 | 49 |  |  |  |  | 25
D4 | Coding | D2, D3 | 10 | 50 | 99 |  | 10 | 40 |  | 40
D5 | Write documentation | D4 | 15 | 15 | 142 | 15
D6 | Unit testing | D4 | 18 | 18 | 117 |  |  | 18 |  | 18
D7 | System testing | D6 | 25 | 25 | 142 |  |  |  |  | 25
D8 | Package deliverables | D5, D7 | 6 | 12 | 154 | 6 |  |  |  | 12
E | Survey potential market | B, C | 10 | 15 | 159 | 10 |  |  | 15
F | Develop pricing plan | D8, E | 10 | 10 | 169 | 10
G | Develop implementation plan | A, D8 | 15 | 15 | 169 | 15 |  |  |  | 15
H | Write client proposal | F, G | 10 | 10 | 179 | 10
|  | Total: | 199 | 271 | 1614

## Project Plan
taskID | task | predecessorTaskIDs | bestCaseHours | expectedHours | worstCaseHours | projectManager | frontendDeveloper | backendDeveloper | dataScientist | dataEngineer
A | Describe product |  | 6 | 6 | 6 | 6
B | Develop marketing strategy |  | 15 | 15 | 144 | 15
C | Design brochure | A | 12 | 12 | 12 | 4 | 12
D | Develop product prototype
D1 | Requirements analysis | A | 18 | 18 | 24 | 8 |  |  | 8
D2 | Software design | D1 | 4 | 25 | 49 |  | 15 |  |  | 8
D3 | System design | D1 | 25 | 25 | 49 |  |  | 25 |  | 10
D4 | Coding | D2, D3 | 10 | 50 | 99 |  | 10 | 40
D5 | Write documentation | D4 | 15 | 15 | 142 | 15
D6 | Unit testing | D4 | 18 | 18 | 117 |  | 18 |  |  | 40
D7 | System testing | D6 | 25 | 25 | 142 |  |  | 25
D8 | Package deliverables | D5, D7 | 6 | 12 | 154 | 6 |  |  | 12 | 18
E | Survey potential market | B, C | 10 | 15 | 159 | 10 |  |  | 15
F | Develop pricing plan | D8, E | 10 | 10 | 169 | 10
G | Develop implementation plan | A, D8 | 15 | 15 | 169 | 15 |  |  |  | 15
H | Write client proposal | F, G | 10 | 10 | 179 | 10

## Expected Gantt Chart
Task ID | Predecessor | Duruation | 0 | 6 | 9 | 12 | 15 | 18 | 21 | 24 | 27 | 30 | 33 | 36 | 39 | 42 | 45 | 48 | 51 | 54 | 57 | 60 | 63 | 66 | 69 | 72 | 75 | 78 | 81 | 84 | 87 | 90 | 93 | 96 | 99 | 102 | 105 | 108 | 111 | 114 | 117 | 120 | 123 | 126 | 129 | 132 | 135 | 138 | 141 | 144 | 147 | 150 | 153 | 156 | 159 | 162 | 165 | 168 | 171 | 174 | 177 | 180
A |  | 6 | bar: 6
B |  | 15 | bar: 6 to 15
C | A | 12 | bar: 9 to 18
D
D1 | A | 18 | bar: 9 to 24
D2 | D1 | 25 | bar: 27 to 48
D3 | D1 | 25 | bar: 27 to 48
D4 | D2, D3 | 50 | bar: 51 to 99
D5 | D4 | 15 | bar: 102 to 114
D6 | D4 | 18 | bar: 102 to 117
D7 | D6 | 25 | bar: 120 to 141
D8 | D5, D7 | 12 | bar: 144 to 153
E | B, C | 15 | bar: 21 to 33
F | D8, E | 10 | bar: 156 to 165
G | A, D8 | 15 | bar: 156 to 168
H | F, G | 10 | bar: 171 to 180
Project Start

## Best Case Gantt Chart
Task ID | Predecessor | Duruation | 0 | 6 | 9 | 12 | 15 | 18 | 21 | 24 | 27 | 30 | 33 | 36 | 39 | 42 | 45 | 48 | 51 | 54 | 57 | 60 | 63 | 66 | 69 | 72 | 75 | 78 | 81 | 84 | 87 | 90 | 93 | 96 | 99 | 102 | 105 | 108 | 111 | 114 | 117 | 120 | 123 | 126 | 129 | 133
A |  | 6 | bar: 6
B |  | 15 | bar: 6 to 15
C | A | 12 | bar: 9 to 18
D
D1 | A | 18 | bar: 9 to 24
D2 | D1 | 4 | bar: 27
D3 | D1 | 25 | bar: 27 to 48
D4 | D2, D3 | 10 | bar: 51 to 60
D5 | D4 | 15 | bar: 63 to 75
D6 | D4 | 18 | bar: 63 to 78
D7 | D6 | 25 | bar: 81 to 102
D8 | D5, D7 | 6 | bar: 105 to 108
E | B, C | 10 | bar: 21 to 27
F | D8, E | 10 | bar: 111 to 117
G | A, D8 | 15 | bar: 111 to 123
H | F, G | 10 | bar: 126 to 133
Project Start

## Worse Case Gantt Chart
Task ID | Predecessor | Duruation | 0 | 6 | 10 | 20 | 30 | 40 | 50 | 60 | 70 | 80 | 90 | 100 | 110 | 120 | 130 | 140 | 150 | 160 | 170 | 180 | 190 | 200 | 210 | 220 | 230 | 240 | 250 | 260 | 270 | 280 | 290 | 300 | 310 | 320 | 330 | 340 | 350 | 360 | 370 | 380 | 390 | 400 | 410 | 420 | 430 | 440 | 450 | 460 | 470 | 480 | 490 | 500 | 510 | 520 | 530 | 540 | 550 | 560 | 570 | 580 | 590 | 600 | 610 | 620 | 630 | 640 | 650 | 660 | 670 | 680 | 690 | 700 | 710 | 720 | 730 | 740 | 750 | 760 | 770 | 780 | 790 | 800 | 810 | 820 | 830 | 840 | 850 | 860 | 870 | 880 | 890 | 900 | 910 | 920 | 930 | 940
A |  | 6 | bar: 6
B |  | 144 | bar: 6 to 140
C | A | 12 | bar: 10 to 20
D
D1 | A | 24 | bar: 10 to 30
D2 | D1 | 49 | bar: 40 to 80
D3 | D1 | 49 | bar: 40 to 80
D4 | D2, D3 | 99 | bar: 90 to 180
D5 | D4 | 142 | bar: 190 to 320
D6 | D4 | 117 | bar: 190 to 300
D7 | D6 | 142 | bar: 310 to 440
D8 | D5, D7 | 154 | bar: 450 to 590
E | B, C | 159 | bar: 150 to 300
F | D8, E | 169 | bar: 600 to 760
G | A, D8 | 169 | bar: 600 to 760
H | F, G | 179 | bar: 770 to 940
Project Start